## Product Roadmap
Instructions: Based on the scenario, place the Product Features into the phases on the Product Roadmap. The product features should be orderd so that the highest value features are delivered to users first and the simple to implement features are delivered before the more complex features. The product Features are listed in Column A. Each Cell in the four phases of the Product Roadmap has a dropdown list that allows you to select the product features that you want to appear in that phase of the roadmap. Every feature must be added to a Phase of the roadmap.
Product Feature List | Phase 1 | Phase 2 | Phase 3 | Phase 4
Initial Architecture/Database Setup & Design | Initial Architecture/Database Setup & Design
Develop iOS Compatible Mobile App |  |  | Develop iOS Compatible Mobile App
Develop Android Compatible Mobile App |  |  | Develop Android Compatible Mobile App
Develop Web Portal application |  | Develop Web Portal application
Upgrade Database |  |  | Upgrade Database
Security Update |  |  |  | Security Update
Manual Importing | Manual Importing
Automated Integration for Importing |  |  |  | Automated Integration for Importing
Mobile App User Interface Refinement |  |  |  | Mobile App User Interface Refinement
Authentication- Login/Logout | Authentication- Login/Logout
Basic Dashboard with heatmap display | Basic Dashboard with heatmap display
Basic Data Searching Capability | Basic Data Searching Capability
Automated Amber Alerts |  |  |  | Automated Amber Alerts
Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities |  | Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities
User Based Preferences- Save Search & Reports |  | User Based Preferences- Save Search & Reports
Web Portal Redesign |  |  | Web Portal Redesign
Export CSV of Reported Data |  |  | Export CSV of Reported Data
Send Manual Amber Alerts by Region | Send Manual Amber Alerts by Region
Web Report of Data (View only no Export) |  | Web Report of Data (View only no Export)
In-App messaging for Doctors and Patients |  |  |  | In-App messaging for Doctors and Patients

## User Roles
Instructions: Below are 7 user roles that have been identified for the product and a brief description for how each user will interact with the product. These user roles can be used to create user stories in the blue "User Story" tab.
Roles | Personas
CDC Officials | Will use product to determine where to apply funding and send test kits
System Administrators | Responsible for governing all roles of the product. This role is not a health professional. This role maintains and governs the system, the process, and does troubleshooting if other users have problems with their roles and access. This role also publishes product information and ensures that the system is performing as intended.
Patients | Will use the product to report, track, and monitor cases of the outbreak
Test Centers | Will use the product to report test kit usage
Doctors | Will use the product to share successful treatment remedies
Medical Examiners | Will use the product to report deaths caused by outbreak
Healthcare Companies | Will use the product to report test kit production and deliveries

## User Stories
Instructions: Create User Stories and Acceptance Criteria in the sheet using the 7 user roles that have been identified in the yellow user role tab. Two user stories have been provided for you for each role. Create at least 2 more user stories for each role based on the needs of each user. You will have at least 28 total user stories when finished. List at least 2 acceptance criteria for each User Story
As a.. | ....I can... | ...so that... | Completed User Story | Acceptance Criteria (Minimum of 2)
CDC Official | view the number of patients that have reported testing positive | so that I can analyze the outbreak | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | - Patient names are anonymous - User can see a summary of the numbers provided - User must be logged in from a government IP address to view
CDC Official | see a report of the # of test kits that health care companies have created | that I can send funding | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | - User can see a summary of the total number of test kits - User can see a summary of the number of test kits produced by healthcare company - User can see the names of the health care company - User can see amount of funds sent to each health care company
Doctor | add the name of patients I have treated | I can add treatments | As a Doctor I can add the name of patients I have treated so that I can add treatments . | - Alpha Numeric characters are allowed - Patient First and Last Name required - Patient DOB required - Patient Location Required - Patient Gender is optional
Doctor | login to the system | I can enter patient treatment information | As a Doctor I can login to the system so that I can enter patient treatment information. | - User name and email address required - User is locked out after 3 incorrect entries
Healthcare Company | add the number of test kits produced | the CDC can determine where test kits should be sent | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | - Only numeric characters allowed - User can see data that previously entered
Healthcare Company | reset my password by myself | that I can login again. | As a Healthcare Company I can reset my password by myself so that that I can login again. . | - User must verify email address - User must verify answer security question to reset password
Medical Examiner | add a person's gender | deaths can be tracked by gender | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | - User can select from list of genders - User can update gender selection - Users gender selection is not shared with CDC Officials
Medical Examiner | am automatically logged out of the system | no one can access my account | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | - Timeout occurs after 15 mins of inactivity - After timeout user is returned to login page
Patient | change my test results | the system data is accurate | As a Patient I can change my test results so that the system data is accurate. | - User can modify test results twice - Doctors are notified when a patient changes test results
Patient | enter any stores that I visited 3 days before testing positive | others are aware of their potential exposure to the virus | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | - Option only visible for patients that report positve test - Can specify store name, date entered, city, and state
System Administrator | give access to the system | users can access,import, share data. | As a System Administrator I can give access to the system so that users can access,import, share data.. | - First and Last Name required - Enter email addresses - Gmail email address are not allowed access
System Administrator | remove access | users are not able to access the system | As a System Administrator I can remove access so that users are not able to access the system. | - Removed user recieves email confirmation of removal - Removed user can't login once removed - System administrator must confirm the user that they are removing before leaving the page
Test Center | update/change the number of test kits recieved | data is accurate | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | - Only allow update one time - Make user confirm change before leaving the page
Test Center | I want to be notified when my stock falls before a certain level, | I can proactively order additional testing supplies | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | System notifies User by email - User can set number that stock must reach for email to be sent - System notifies User upon login that stock is low
CDC Official | View a heatmap display of outbreak | so that I can determine the region that needs urgently kit supply | As a CDC Official I can View a heatmap display of outbreak so that so that I can determine the region that needs urgently kit supply. | User can segment by region/area Zoom in /out display the heatmap as a map
CDC Official | I want to receive an alert from specific area | I can urgently arrange funding. | As a CDC Official I can I want to receive an alert from specific area so that I can urgently arrange funding.. | The system can notify me with details about the location and status user view the area location -see a detailed report
Doctor | write a medical instructions and advice | Patients and people will have a medical instructions to follow ,knowledge about sysmtoms. | As a Doctor I can write a medical instructions and advice so that Patients and people will have a medical instructions to follow ,knowledge about sysmtoms. . | Users can write, delete and update articles - set the priority f the advice
Doctor | report successful treatment | research has accurate data | As a Doctor I can report successful treatment so that research has accurate data. | User can upload a report (pdf,word)/
Healthcare Company | report the delivery status of the test kits. | CDC and test center have the delivery and supply updated data | As a Healthcare Company I can report the delivery status of the test kits. so that CDC and test center have the delivery and supply updated data. | Users can change the delivery status Set the expected day of delivery Upload the delivery roadmap.
Healthcare Company | report any change in the production status | CDC be informed about the production status and take actions in advance | As a Healthcare Company I can report any change in the production status so that CDC be informed about the production status and take actions in advance. | User can report any problem through notifications and email /user can update once the prolem solved /user can upload a detailed report about the problem
Medical Examiner | add person's birth date | deaths can be tracked by age | As a Medical Examiner I can add person's birth date so that deaths can be tracked by age. | Users can select their birth date from the drop-down calendar
Medical Examiner | Attach a medical report of the death reasson | data is accurate | As a Medical Examiner I can Attach a medical report of the death reasson so that data is accurate. | User can upload the death clinical exams report/ user can add notes related/user can upload files(Pdf,word)
Patient | read instructions and advice written by doctors | I have a medical reference about behavior to follow | As a Patient I can read instructions and advice written by doctors so that I have a medical reference about behavior to follow. | User can reach the articles page on the web / User can see articales segmanted .
Patient | I can contact doctor for more information | I can follow accurate medical instruction | As a Patient I can I can contact doctor for more information so that I can follow accurate medical instruction. | User can call or message the doctor /user can call on a hot line.
System Administrator | can change and update user permission | user has the permission needed for his determined mission | As a System Administrator I can can change and update user permission so that user has the permission needed for his determined mission. | user can change the permissions/drop-down list of all the permissions/see current users permissions
System Administrator | I have the ability to monitor the system | quickly solve the system prolems. | As a System Administrator I can I have the ability to monitor the system so that quickly solve the system prolems.. | user can access the monitor page / receive notification about any problem
Test Center | can send an alert to CDC when the low level of kits test stock not solved | CDC can arrange a quick supply | As a Test Center I can can send an alert to CDC when the low level of kits test stock not solved so that CDC can arrange a quick supply. | User can see the alert button at a certain level of kits/user can set the wanted day of delivery
Test Center | I can track the supply process and date of delivery | always been updated | As a Test Center I can I can track the supply process and date of delivery so that always been updated . | user sees the time of delivery - see the status of delivery (processing,on the way,delivered)

## Release Plan & MVP Plan
Instructions: Create a Release & MVP Plan in this sheet. Copy your 10 Release 1 (MVP) user stories from Priority sheet into column C, Rows 3-12 below in the appropriate sprint. Copy your 10 Release 2 user stories from Priority sheet into column C, Rows 13-22 below in the appropriate sprint. Copy your 5 Release 3 user stories from Priority sheet into column C, Rows 23-27 below in the appropriate sprint.
Releases | Sprints | User Story | Story Points
Release 1- MVP | Sprint 1 | As a System Administrator I can give access to the system so that users can access,import, share data. | 2
|  | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | 3
|  | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | 3
| Sprint 2 | As a CDC Official I can View a heatmap display of outbreak so that so that I can determine the region that needs urgently kit supply. | 5
|  | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | 0.5
|  | As a Doctor I can login to the system so that I can enter patient treatment information. | 2
|  | As a System Administrator I can I have the ability to monitor the system so that quickly solve the system prolems.. | 0.5
| Sprint 3 | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | 5
|  | As a Test Center I can can send an alert to CDC when the low level of kits test stock not solved so that CDC can arrange a quick supply. | 2
|  | As a Medical Examiner I can add person's birth date so that deaths can be tracked by age. | 1
Release 2 | Sprint 4 | As a Healthcare Company I can report the delivery status of the test kits. so that CDC and test center have the delivery and supply updated data. | 5
|  | As a Doctor I can add the name of patients I have treated so that I can add treatments . | 0.5
|  | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | 1
|  | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | 1
|  | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | 0.5
| Sprint 5 | As a Doctor I can write a medical instructions and advice so that Patients and people will have a medical instructions to follow ,knowledge about sysmtoms. . | 1
|  | As a Patient I can change my test results so that the system data is accurate. | 2
|  | As a Medical Examiner I can Attach a medical report of the death reasson so that data is accurate. | 2
|  | As a Patient I can read instructions and advice written by doctors so that I have a medical reference about behavior to follow. | 1
|  | As a Healthcare Company I can report any change in the production status so that CDC be informed about the production status and take actions in advance. | 3
Release 3 | Sprint 6 | As a Doctor I can report successful treatment so that research has accurate data. | 3
|  | As a Test Center I can I can track the supply process and date of delivery so that always been updated . | 5
| Sprint 7 | As a CDC Official I can I want to receive an alert from specific area so that I can urgently arrange funding.. | 2
|  | As a System Administrator I can remove access so that users are not able to access the system. | 0.5
|  | As a System Administrator I can can change and update user permission so that user has the permission needed for his determined mission. | 5

## Priority
Instructions: All of the user stories that you created will automatically appear in this sheet. Prioritize the user stories so that the highest value features are delivered to users first using the following parameters: There are 3 Releases- Release 1-MVP, Release 2, and Release 3 (All contained in the dropdown menus in Column D) - Release 1 (MVP) contains 3 sprints. The release can only have 10 user stories within the 3 sprints - Sprint 1 will have 3 user stories - Sprint 2 will have 4 user stories - Sprint 3 will have 3 user stories - Release 2 contains 2 sprints. The release can only have 10 user stories within the 2 sprints - Sprint 4 and Sprint 5 will each have 5 user stories - Release 3 contains 2 sprints. The release can only have 5 user stories within the 2 sprints - Sprint 6 will have 2 user stories - Sprint 7 will have 3 user stories - All remaining user stories are assigned to "Backlog for Future Release" - Assign the sprint that the user stories will be in within that particular release in Column E. If it is is "Backlog for Future Release" the user story doesn't need to be assigned a sprint. |  |  |  |  | Hints/Tips: - Question if a user role has too much functionality to be in the MVP release. - Question what is a nice-to-have vs high-value based on the scenario and vision. - Question if you should trade off- what is the worst thing that could happen if the user had to wait for that functionality to come later. - Refine, rewrite, or delete a user story in the blue user story tab if it doesn’t fit into your Release or MVP plan
Role | User Story | Acceptance Critieria | Release | Sprint | Sprint | Release 1-MVP Total Stories =10 | Release 2 Total Stories =10 | Release 3 Total Stories =5 | Backlog for Future Release
CDC Official | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | - Patient names are anonymous - User can see a summary of the numbers provided - User must be logged in from a government IP address to view | Release 1 (MVP) | 2 | 1 Total Stories = 3 | 3
CDC Official | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | - User can see a summary of the total number of test kits - User can see a summary of the number of test kits produced by healthcare company - User can see the names of the health care company - User can see amount of funds sent to each health care company | Release 1 (MVP) | 1 | 2 Total Stories = 4 | 4
Doctor | As a Doctor I can add the name of patients I have treated so that I can add treatments . | - Alpha Numeric characters are allowed - Patient First and Last Name required - Patient DOB required - Patient Location Required - Patient Gender is optional | Release 2 | 4 | 3 Total Stories = 3 | 3
Doctor | As a Doctor I can login to the system so that I can enter patient treatment information. | - User name and email address required - User is locked out after 3 incorrect entries | Release 1 (MVP) | 2 | 4 Total Stories = 5 |  | 5
Healthcare Company | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | - Only numeric characters allowed - User can see data that previously entered | Release 1 (MVP) | 1 | 5 Total Stories = 5 |  | 5
Healthcare Company | As a Healthcare Company I can reset my password by myself so that that I can login again. . | - User must verify email address - User must verify answer security question to reset password | Backlog for Future Release |  | 6 Total Stories = 2 |  |  | 2
Medical Examiner | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | - User can select from list of genders - User can update gender selection - Users gender selection is not shared with CDC Officials | Release 2 | 4 | 7 Total Stories = 3 |  |  | 3
Medical Examiner | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | - Timeout occurs after 15 mins of inactivity - After timeout user is returned to login page | Backlog for Future Release |  | Sum | 10 | 10 | 5
Patient | As a Patient I can change my test results so that the system data is accurate. | - User can modify test results twice - Doctors are notified when a patient changes test results | Release 2 | 5 | Total | 10 | 10 | 5 | 3
Patient | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | - Option only visible for patients that report positve test - Can specify store name, date entered, city, and state | Release 2 | 4 | SUM = TOTAL | #NAME? | #NAME? | #NAME?
System Administrator | As a System Administrator I can give access to the system so that users can access,import, share data.. | - First and Last Name required - Enter email addresses - Gmail email address are not allowed access | Release 1 (MVP) | 1
System Administrator | As a System Administrator I can remove access so that users are not able to access the system. | - Removed user recieves email confirmation of removal - Removed user can't login once removed - System administrator must confirm the user that they are removing before leaving the page | Release 3 | 7
Test Center | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | - Only allow update one time - Make user confirm change before leaving the page | Release 2 | 4
Test Center | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | System notifies User by email - User can set number that stock must reach for email to be sent - System notifies User upon login that stock is low | Release 1 (MVP) | 3
CDC Official | As a CDC Official I can View a heatmap display of outbreak so that so that I can determine the region that needs urgently kit supply. | User can segment by region/area Zoom in /out display the heatmap as a map | Release 1 (MVP) | 2
CDC Official | As a CDC Official I can I want to receive an alert from specific area so that I can urgently arrange funding.. | The system can notify me with details about the location and status user view the area location -see a detailed report | Release 3 | 7
Doctor | As a Doctor I can write a medical instructions and advice so that Patients and people will have a medical instructions to follow ,knowledge about sysmtoms. . | Users can write, delete and update articles - set the priority f the advice | Release 2 | 5
Doctor | As a Doctor I can report successful treatment so that research has accurate data. | User can upload a report (pdf,word)/ | Release 3 | 6
Healthcare Company | As a Healthcare Company I can report the delivery status of the test kits. so that CDC and test center have the delivery and supply updated data. | Users can change the delivery status Set the expected day of delivery Upload the delivery roadmap. | Release 2 | 4
Healthcare Company | As a Healthcare Company I can report any change in the production status so that CDC be informed about the production status and take actions in advance. | User can report any problem through notifications and email /user can update once the prolem solved /user can upload a detailed report about the problem | Release 2 | 5
Medical Examiner | As a Medical Examiner I can add person's birth date so that deaths can be tracked by age. | Users can select their birth date from the drop-down calendar | Release 1 (MVP) | 3
Medical Examiner | As a Medical Examiner I can Attach a medical report of the death reasson so that data is accurate. | User can upload the death clinical exams report/ user can add notes related/user can upload files(Pdf,word) | Release 2 | 5
Patient | As a Patient I can read instructions and advice written by doctors so that I have a medical reference about behavior to follow. | User can reach the articles page on the web / User can see articales segmanted . | Release 2 | 5
Patient | As a Patient I can I can contact doctor for more information so that I can follow accurate medical instruction. | User can call or message the doctor /user can call on a hot line. | Backlog for Future Release
System Administrator | As a System Administrator I can can change and update user permission so that user has the permission needed for his determined mission. | user can change the permissions/drop-down list of all the permissions/see current users permissions | Release 3 | 7
System Administrator | As a System Administrator I can I have the ability to monitor the system so that quickly solve the system prolems.. | user can access the monitor page / receive notification about any problem | Release 1 (MVP) | 2
Test Center | As a Test Center I can can send an alert to CDC when the low level of kits test stock not solved so that CDC can arrange a quick supply. | User can see the alert button at a certain level of kits/user can set the wanted day of delivery | Release 1 (MVP) | 3
Test Center | As a Test Center I can I can track the supply process and date of delivery so that always been updated . | user sees the time of delivery - see the status of delivery (processing,on the way,delivered) | Release 3 | 6